|  |
| --- |
| **Project Details** |
| Year: | 2017 |
| Parent Department: |  |
| Name of Contracting Body: | South Dublin County Council |
| Name of Project/Description: | Construction of Rapid build Social Housing Development at St Aidans, Brookfield Road/R136, Tallaght, Dublin 24 |
| **Procurement Details** |
| Advertisement Date: | 22 December 2016 |
| Tender Advertised in: | OJEU & [www.etenders.gov.ie](http://www.etenders.gov.ie)  |
| Awarded to: | John Sisk & Son (Holdings) Ltd |
| EU Contract Award Notice Date: | 22 August 2017 |
| Contract Price: | € 13,531,903.39 |
| **Progress** |
| Start Date: | August 2017 |
| Expected Date of Completion per Contract: | May 2019 |
| Spend in Year under Review: | €7,626,999.51 (Incl Vat) |
| Cumulative Spend to End of Year: | €7,626,999.51 |
| Projected Final Cost: | €13,531,903 |
| Value of Contract Variations: | N/A |
| Date of Completion: |  |
| **Outputs** |
| Expected Output on Completion | 85 Units |
| Output Achieved to date | 47 Units (May 2018) |

|  |
| --- |
| **Project Details** |
| Year: | 2017 |
| Parent Department: |  |
| Name of Contracting Body: | South Dublin County Council |
| Name of Project/Description: | Adamstown Road (R120) and Nangor Road (R134) Improvement Scheme Main Contractor  |
| **Procurement Details** |
| Advertisement Date: | 22 January 2016 |
| Tender Advertised in: | OJEU & [www.etenders.gov.ie](http://www.etenders.gov.ie) |
| Awarded to: | Wills Bros |
| EU Contract Award Notice Date: |  |
| Contract Price: | € 12,437,500 |
| **Progress** |
| Start Date: | November 2017 |
| Expected Date of Completion per Contract: | February 2019 |
| Spend in Year under Review: | €1,666,109.65 |
| Cumulative Spend to End of Year: | €1,666,109.65 |
| Projected Final Cost: | €12,437,500.00 |
| Value of Contract Variations: | N/A |
| Date of Completion: |  |
| **Outputs** |
| Expected Output on Completion | Road Improvement scheme as per Tender specification.   |
| Output Achieved to date | 40% Completed to date and on schedule |