| Year: | 2025 |
| --- | --- |
| Parent Department: | Housing Department |
| Name of Contracting Body: | South Dublin County Council |
| Name of Project/Description: | Design and Delivery of a Sustainable Integrated Mixed Tenure Housing Development at Kilcarbery, Clondalkin, Dublin 22. |
| Procurement Details |  |
| Advertisement Date: | 26/04/2017 |
| Tender Advertised in: | OJEU & ETenders |
| Awarded to: | Adwood Ltd |
| EU Contract Award Notice Date: | 15/03/2021 |
| Contract Price: | €51,414,648 |
| Progress |  |
| Start Date: | April 2021 |
| Expected Date of Completion per Contract: | 2025 |
| Spend in Year under Review: | €11,977,388 |
| Cumulative Spend to End of Year: | €52,684,266 |
| Projected Final Cost: | €55,354,659 |
| Value of Contract Variations: | €3,939,933 |
| Date of Completion: | 2025 |
| Outputs |  |
| Expected Output on Completion | 310 social housing units. |
| Output Achieved to date | 78 social housing units delivered in 2022, 103 units delivered in 2023, 82 in 2024 & 47 in 2025. |

| Year: | 2025 |
| --- | --- |
| Parent Department: | Housing Department |
| Name of Contracting Body: | South Dublin County Council |
| Name of Project/Description: | Design and delivery of a sustainable integrated mixed tenure housing development at Killinarden Hill Tallaght, Dublin 24. |
| Procurement Details |  |
| Advertisement Date: | 03/07/2020 |
| Tender Advertised in: | Etenders & OJEU |
| Awarded to: | The Arden Team |
| EU Contract Award Notice Date: | 01/06/2022 |
| Contract Price: | €46,133,822 |
| Progress |  |
| Start Date: | Q3 2024 |
| Expected Date of Completion per Contract: | Q4 2030 |
| Spend in Year under Review: | €38,776 |
| Cumulative Spend to End of Year: | €38,776 |
| Projected Final Cost: | €46,133,822 |
| Value of Contract Variations: | 0.00 |
| Date of Completion: | 2030 |
| Outputs |  |
| Expected Output on Completion | 125 Social Housing Units |
| Output Achieved to date | Under construction |

| Year: | 2025 |
| --- | --- |
| Parent Department: | Housing, Social, and Community Development |
| Name of Contracting Body: | South Dublin County Council |
| Name of Project/Description: | Design and delivery of mixed tenure housing development at Clonburris (Phase 2), Clondalkin, Dublin 22 |
| Procurement Details |  |
| Advertisement Date: | 17/08/2022 |
| Tender Advertised in: | eTenders &OJEU |
| Awarded to: | Cunningham Contracts Ltd |
| EU Contract Award Notice Date: | 26/09/2023 |
| Contract Price: | €38,987,750 |
| Progress |  |
| Start Date: | Q3 2023 |
| Expected Date of Completion per Contract: | 2025 |
| Spend in Year under Review: | €19,863,660 |
| Cumulative Spend to End of Year: | €38,953,356 |
| Projected Final Cost: | €40,482,990 |
| Value of Contract Variations: | €40,482,990 |
| Date of Completion: | 2025 |
| Outputs |  |
| Expected Output on Completion | 56 social housing units and 60 Affordable housing units |
| Output Achieved to date | 56 social housing units and 60 Affordable housing units |

| Year: | 2025 |
| --- | --- |
| Parent Department: | Housing, Social, and Community Development |
| Name of Contracting Body: | South Dublin County Council |
| Name of Project/Description: | Design and delivery of a cost rental housing at Belgard Square, Tallaght , Dublin 24 |
| Procurement Details |  |
| Advertisement Date: | 1st March 2021 |
| Tender Advertised in: | OJEU and eTenders |
| Awarded to: | J. J. Rhatigan & Co. Ltd |
| EU Contract Award Notice Date: | 07/03/2023 |
| Contract Price: | €53,997,373 |
| Progress |  |
| Start Date: | Q1 2023 |
| Expected Date of Completion per Contract: | Q1 2025 |
| Spend in Year under Review: | €2,626,574 |
| Cumulative Spend to End of Year: | €53,370,725 |
| Projected Final Cost: | €53,999,800 |
| Value of Contract Variations: | 0.00 |
| Date of Completion: | 2025 |
| Outputs |  |
| Expected Output on Completion | 133 Cost rental Apartments |
| Output Achieved to date | 133 Cost rental Apartments |
| Year: | 2025 |
| Parent Department: | Housing, Social, and Community Development |
| Name of Contracting Body: | South Dublin County Council |
| Name of Project/Description: | Design and Build of 284 Housing Units at Kishoge Gardens, Clonburris (Phase 1) |
| Procurement Details |  |
| Advertisement Date: | 02/09/2024 |
| Tender Advertised in: | Etenders & OJEU |
| Awarded to: | Cunningham Contracts Ltd |
| EU Contract Award Notice Date: | 16/06/2025 |
| Contract Price: | €98,089,400 |
| Progress |  |
| Start Date: | Q4.2025 |
| Expected Date of Completion per Contract: | Q1.2028 |
| Spend in Year under Review: | €1,246,734 |
| Cumulative Spend to End of Year: | €1,246,734 |
| Projected Final Cost: | €98,089,400 |
| Value of Contract Variations: | €0.00 |
| Date of Completion: | 2028 |
| Outputs |  |
| Expected Output on Completion | 93 Social Housing Units, 93 Affordable Purchase Units, 83 Cost Rental Units & 15 TAU |
| Output Achieved to date | Under construction |

| Year: | 2025 |
| --- | --- |
| Parent Department: | Housing, Social, and Community Development |
| Name of Contracting Body: | South Dublin County Council |
| Name of Project/Description: | Construction of 27 no. age friendly residential units & associated development works at Deansrath Melrose, Clondalkin, Dublin 22 |
| Procurement Details |  |
| Advertisement Date: | 22/10/2024 |
| Tender Advertised in: | Etenders & OJEU |
| Awarded to: | Cleary & Doyle Construction |
| EU Contract Award Notice Date: | 16/09/2025 |
| Contract Price: | €10,382,627 |
| Progress |  |
| Start Date: | Q1.2025 |
| Expected Date of Completion per Contract: | Q4.2026 |
| Spend in Year under Review: | €3,015,938.47 |
| Cumulative Spend to End of Year: |  |
| Projected Final Cost: | €10,382,627 |
| Value of Contract Variations: |  |
| Date of Completion: | 2026 |
| Outputs |  |
| Expected Output on Completion | 27 Age Friendly Social Homes |
| Output Achieved to date | Under construction |