## Sheet1
Developer TIC Submission to SDCC
SharePoint Checklist
| All items to be be submitted in soft copy format unless specified | Corresponding Explanatory Notes
Note: All guidance documents referred to below are available on SDCC's TIC webpage
No. | Item
| Cover Letter (optional) | Stating intention to offer areas/assets to be TIC
1 | CBR Map & Results (Copy of) | Must be submitted at commencement stage and a copy will be on file (CBR tests are used to evaluate subgrade strength for road design)
2 | SDCC TIC Application Form (Copy of) | Original will already have been submitted when initiating TIC
3 | TIC As-Constructed Drawing | Colour-coded as per guidance document SDCC TIC (8)
4 | Wayleaves Executed | Drawings & legal text (Only if wayleaves are applicable)
5 | CCTV Survey (Post-Repair) | Soft copy of camera survey footage
| CCTV Report (Post-Repair) | A post repair report will have few if any issues presenting
6 | Manhole Survey & Report including Manhole Cards (Post-Repair) | One page for each manhole as per guidance document SDCC TIC (11)
7 | Letter of Compliance from SDCC Water Services | In reference to conditions to the laying of watermain, and pipe pressure tests as witnessed by SDCC Water Services (Storm & Foul)
8 | Letter of Compliance from Consulting Engineer - Attenuation | Stating system is compliant, manufacturers details, system has been installed to the manufacturers GL, and guarantee period provided with end date specified.
9 | Letter of Compliance from SDCC Pollution Control | Stating no pollution nor cross-contamination of drainage lines was found following drainage network surveys by SDCC WS
10 | Completed Irish Water MOU Schedules 1 & 2 | Memorandum of Understanding - See guidance document - SDCC TIC (13)
11 | IW MOU - Information Checklist | See guidance document SDCC TIC (13b) - Lists the 10no. items required to satisfy the Irish Water TIC requirments
12 | Fire Hydrant Report | To be completed by a Competent & Independent Person (Must demonstrate compliance; include distances & flow rates)
13 | Letter of Approval from SDCC Public Realm | See guidance document SDCC TIC (19) - Public Realm TIC requirements
14 | Letter of Compliance from SDCC Public Lighting Section | Stating that the Public Lighting being offered has met the taking in charge standards of the SDCC Public Lighting Section, and all other relevant standards
15 | Road Pavement Cores - Test Results & Report | To be completed by an Independent Company
16 | Letter of Compliance from SDCC TIC - Pavement Defects | Stating road pavement and footpaths were defect free at the time of TIC
17 | Letter of Compliance from Consulting Engineer re Boundary Walls | Stating compliance with the IS 325 standard has been met
18 | Letter of Compliance from SDCC Traffic Section re Nameplates | Stating nameplates have been installed in accordance with the SDCC Nameplates Specification
19 | Letter of Compliance from Consulting Engineer re Civil Works | Stating civil works have been carried out in accordance with planning permission and all relevant standards of the day
20 | Professional Indemnity Insurance Certificate for Consulting Engineer | Submit a copy
21 | Safety File | A requirement since Dec 15th 2020